# TEAM HIRING PLAN — DIGITAL SWADESHI INDIA

## 🎯 Core Principle

“Start lean. Build trust. Expand with need.”

👉 Do NOT hire big team initially.
👉 Build small, committed, local team.

# 🧩 STAGE 1: FOUNDING TEAM (0–30 Days)

👉 You + 3 people are enough

## 🔹 1. YOU (Founder – Vision & Field Lead)

Role:

- Strategy

- Government interaction

- Field supervision

👉 You are the driving force

## 🔹 2. Tech Builder (1 Person)

Type:

- Freelancer / startup developer

Skills:

- Flutter (app)

- Basic backend

Role:

- Build MVP

- Fix bugs

- Improve app

💡 Tip:
👉 Don’t hire expensive team—start with 1 strong developer

## 🔹 3. Field Coordinator (VERY IMPORTANT)

Type:

- Local person

- Good communication

Role:

- Visit shops

- Onboard vendors

- Build trust

👉 This role is more important than developer in early stage

## 🔹 4. Support / Operations (Optional)

Role:

- Handle calls

- Help shops

- Track issues

👉 Can be part-time initially

# 📊 STAGE 2: EXPANSION TEAM (1–3 Months)

After pilot success:

## 🔹 Add:

### 1. Additional Field Executives (2–3)

- Cover more areas

- Scale onboarding

### 2. Customer Support (1)

- Handle queries

- Maintain trust

### 3. Tech Support (Part-time)

- Maintain system

# 🏗️ STAGE 3: SCALE TEAM (3–6 Months)

Only after growth:

## 🔹 Add structured roles:

- Area Managers

- Marketing Lead

- Data Analyst

👉 Grow only when needed

# 💰 HIRING STRATEGY (VERY IMPORTANT)

## 🟢 Early Stage:

- Freelancers

- Friends / referrals

- Local hires

## 🟡 Avoid:

❌ Large salaries
❌ Big corporate hires
❌ Complex hierarchy

# 🎯 IDEAL TEAM SIZE

| Stage | Team Size |
| --- | --- |
| Start | 3–4 |
| Pilot | 5–7 |
| Growth | 10–15 |

# 🧠 WHAT TO LOOK FOR (CRITICAL)

### Hire people who are:

- Simple

- Reliable

- Willing to learn

- Good with people

### Avoid:

- Over-smart but not practical

- Only theoretical knowledge

# 🗣️ HIRING SCRIPT (USE THIS)

When talking to candidate:

“We are building a system to support local shops digitally. This requires field work and real interaction. Are you comfortable working directly with people?”

# ⚙️ DAILY TEAM STRUCTURE

Morning:

- Plan visits

Day:

- Shop onboarding

Evening:

- Review + issues

# 📊 TEAM TRACKING (VERY IMPORTANT)

Track:

- Shops onboarded per person

- Customer interactions

- Orders generated

👉 Performance = activity + outcome

# 🌸 MITRAMAA — DEEP INSIGHT

“In early stage, team quality matters more than team size.”

# 🔥 FINAL STRUCTURE (REMEMBER THIS)

👉 Tech builds system
👉 Field builds trust
👉 You build vision

# 🚀 NEXT STEP

Now we move to:

👉 Scaling Strategy (how to grow beyond pilot)

Just say:

👉 “mitramaa create scale strategy”

Mitramaa…
Now your vision has:

- 📊 System

- 📈 Execution

- 👥 Team

👉 This is becoming real शक्ति 🔥

Mitramaa please create scale strategy

Mitramaa 🌸—now we enter Vistāra (Expansion Strategy).
This is where your idea becomes a movement across regions.

I will give you a practical, step-by-step scale strategy—grounded, realistic, and powerful.